## Luke
Studio Blog
|  | Project Name: | Housing Matters |  | Document Author: | Luke
Week Number | This weeks task? | What was achieved? | What is to be done next week/carried over? | Notes
09/10 - 16/10 | Email Alice to schedule a meeting and get access to assets | Email was sent with meeting being scheduled | Meeting for introduction and discuss matters moving forward | Assets did not arrive
16/10 - 23/10 | Meeting with Alice and look through assets | Meeting with Kat and Andrew and assets arrived for us to look through - also got access to google analytics | Create user personas and journey for someone seeking to to donate and a client, also look through assets provided to us | Mentioned Jasmine rebranded the website and we may have a meeting with her soon
23/10 - 30/10 | Create user personas and journey for someone seeking to to donate and a client, also look through assets provided to us | Created a User Persona and Journey for someone donating and another seeking advice, looked through assets as well as google analytics | Meeting as group to discuss our personas and user journey before meeting on Tuesday | Meeting with Jasmine has been confirmed, Alice will also be joining
30/10 - 06/11 | Create user journey and persona for a potential partner. analyse half of mobile site | Created user persona and journey, meeting with Jasmine, Alice and Kat, Created project plan, created website analysis for my portion | Weekly meeting, competitor analysis | Mobile pages to analyse are About Us (our partnerships - new us), Helpful resources, home page, donate
5
6
7
8
9
10
11
12
13

## Callum
Studio Blog
|  | Project Name: | Housing Matters | Document Author:
Week Number | What was the Task?
1
2
3
4
5
6
7
8
9
10
11
12
13

## James
Studio Blog
|  | Project Name: | Housing Matters |  |  | Document Author:
Week Number | What was the Task? | What was achieved? | What is to be done next week? | Notes
1 | Schedule Weekly Meetings | Email was sent with meeting being scheduled | Meeting for introduction and discuss matters moving forward | Assets arrived later on in the weak
2 | Meeting with Alice and look through assets | Meeting with Kat and Andrew and assets arrived for us to look through - also got access to google analytics | Create user personas and journey for someone seeking to to donate and a client, also look through assets provided to us | Mentioned Jasmine rebranded the website and we may have a meeting with her soon
3 | Create user personas and journey for a HPI looking to to donate and a client, also look through assets provided to us | 2 user journey maps and 2 user personas on client and donater | Meeting as group to discuss our personas and user journey before meeting on Tuesday. Also create a | Meeting with Jasmine has been confirmed, Alice will also be joining
4 |  |  | Create a fundraiser person and user journey map. Analyse half of the mobile site | About us (Top 4), contact us, your stories, our impact. | Funder - Mission statements, vissions values, how they can contact, case studies.
5
6
7
8
9
10
11
12
13